## Slide 1
TRANSFORMATION LAUNCH READINESS DIAGNOSTIC
Initiative Success Diagnostic
Prepared for: Jordan Ellis, CTO
Meridian Health Systems | June 2026
Initiative: Epic EHR Implementation — Go-Live Target: Q1 2027
CxO Amplify

## Slide 2
IMPORTANT NOTICE
VERDICT: NOT READY TO LAUNCH
Sample Report - 9 of 19 pages. Full report delivered upon engagement completion.

## Slide 3
Executive Flash
VERDICT: NOT READY TO LAUNCH
LAUNCH POSTURE
High-Risk
One Tier 1 hard stop triggered. Q1 2027 cannot be treated as a firm date until launch gates are met.
PRIMARY DERAILER
Scope Discipline
Day One definition not settled. Stakeholders hold divergent expectations. Score: 1.4 / 4.0.
STRONGEST ASSET
Executive Sponsorship
CEO engaged, decisive, and displacing priorities. Score: 3.8 / 4.0. This is the lever that fixes everything else.
LEADERSHIP DECISION REQUIRED
Confirm Q1 2027 only after Day One scope is settled in a leadership working session, business data owners are named, and clinical SME capacity relief is budgeted. Until these three gates are met, Q1 2027 is a planning target, not a commitment.
Scope Discipline (1.4) is the only Tier 1 hard stop — the single finding that independently prevents a firm launch date.
Data Readiness (1.8) is the most time-critical Tier 2 risk — migration planning requires named business owners within 30 days.
Executive sponsorship (3.8) is the organizational lever that makes the hard stops fixable. It needs a clear ask, not convincing.
CxO Amplify

## Slide 4
How This Assessment Works
The Transformation Launch Readiness Diagnostic evaluates twelve dimensions of organizational readiness across three tiers. Scores are based on structured stakeholder responses, project artifact review, and advisor interpretation. This slide explains how findings are produced and how to read the report.
ASSESSMENT INPUTS
— Structured diagnostic instrument — CIO and two senior business peers
— Qualitative open-response questions (seven prompts)
— Project charter, business case, and scope documentation
— SI proposal, implementation timeline, and contract summary
— Governance model and steering committee structure
— Preliminary data migration approach and data inventory
TIER LOGIC — HOW FINDINGS ARE WEIGHTED
Tier 1 — Hard Stops
A critical gap here independently prevents a firm launch date, regardless of overall score. Executive Sponsorship, Business Ownership, Governance, and Scope Discipline.
Tier 2 — Material Risks
Significant gaps here materially increase failure probability. Require active remediation before launch. Organizational Change Capacity, Data Readiness, Process Readiness, Version 1.0 Discipline, Benefits Realization.
Tier 3 — Watch Items
Gaps create friction and should be monitored. Rarely the primary cause of failure on their own. Vendor Relationship, Testing Realism, Organizational Trust.
SCORE SCALE — WHAT THE NUMBERS MEAN
3.5 – 4.0 Strong
Performing at or above required level
2.5 – 3.4 Watch
Functional but with a specific vulnerability
1.5 – 2.4 At Risk
Gap that will impact launch if unaddressed
< 1.5 Critical Gap
Hard stop or near-hard-stop condition
CxO Amplify

## Slide 5
Readiness Dashboard — All Dimensions
One Tier 1 hard stop · Four Tier 2 material risks · Three Tier 3 watch items · Overall readiness: 2.4 / 4.0
Strong (3.5–4.0)
Watch (2.5–3.4)
At Risk (1.5–2.4)
Critical Gap (<1.5)
Dimension
Tier
Score
Status
Trend
Leadership Implication
Executive Sponsorship Quality
T1
3.8
Strong
↑
CEO is displacing priorities for this. The lever that makes everything else fixable.
Business Ownership Clarity
T1
2.8
Watch
→
Ownership claimed publicly. Day-to-day accountability still defaults to IT.
Governance & Decision Velocity
T1
2.6
Watch
↑
Decisions running 3–4 weeks. No fast-track mechanism. Trending positive.
Scope Discipline
T1
1.4
Critical
↓
Day One not agreed. Stakeholders divergent. Informal scope requests accumulating. HARD STOP.
Process Readiness
T2
2.4
At Risk
→
Workflows documented inconsistently. Two key processes under active redesign.
Data Readiness
T2
1.8
At Risk
↓
No business data owners named. Migration untested. Structural gaps not mapped.
Organizational Change Capacity
T2
2.2
At Risk
→
Three parallel initiatives. No backfill planned for clinical SMEs on project team.
Version 1.0 Discipline
T2
1.6
At Risk
→
Stakeholders describe go-live functionality inconsistently. Deferral conversations incomplete.
Benefits Realization
T2
2.0
At Risk
→
Business case built. No named benefit owners. No post-go-live measurement plan.
Vendor & SI Relationship
T3
3.1
Watch
→
Contract actively negotiated. Internal PM has authority. Mid-tier client — appropriate risk profile.
Testing & Cutover Realism
T3
2.5
Watch
→
UAT planned. End-to-end scenarios not defined. No cutover rehearsal scheduled.
Organizational Trust
T3
2.9
Watch
↑
Cautious optimism. Mixed prior track record. No active skeptic disengagement observed.
CxO Amplify

## Slide 6
HARD STOP — Derailer #1 · Tier 1 · Score: 1.4 / 4.0
Scope Discipline
WHAT WE FOUND
When asked to describe what the Epic system will deliver on go-live day, Meridian's three most senior clinical stakeholders gave materially different answers. The scope definition exists as a project document. It does not exist as a shared organizational understanding. Multiple requests for additional functionality have been discussed informally — none have been formally evaluated or deferred through a documented change control process.
TRIPWIRE — IF THIS DESCRIBES YOUR REALITY
When a senior clinical leader mentions a capability they're expecting in the first release, the room gets quiet rather than redirecting them to the deferred list. Everyone knows the list. Nobody enforces it. The implicit deal is that the scope conversation will get resolved "closer to go-live" — which means it won't get resolved until the SI is billing for changes that weren't in the plan.
CONSEQUENCE IF UNRESOLVED
Scope expansion does not announce itself. It accumulates. Every informal accommodation creates a budget and timeline assumption that will be violated. The SI's change order provisions exist precisely because this pattern is universal in engagements where scope is not formally governed. This is a known failure sequence in large enterprise implementations — informal scope accommodation becomes formal budget and timeline variance, discovered under project pressure instead of before it.
THE FIRST MOVE — BEFORE ANYTHING ELSE
Schedule a half-day working session with the CEO, CMO, and CFO — not the project team. Walk through the Day One scope document line by line. For every item: in or out. Document it. Distribute it. This is a leadership alignment exercise, not a project management one. The CEO's signature on a scope document does not equal organizational understanding. This meeting creates it.
Assessment note: This finding reflects an internal alignment gap — the scope challenge originates within the leadership team, not from external board pressure. The debrief conversation will identify which leaders are driving informal scope requests and what governance mechanism would give the program director standing to redirect them.
Score: 1.4 / 4.0
Critical Gap — Hard Stop
CxO Amplify

## Slide 7
Strengths Snapshot
Three dimensions are genuinely strong. They are not included here for balance — they are the organizational assets that make the derailers fixable. Without strong executive sponsorship, this assessment would recommend pausing the launch timeline. Use these assets deliberately.
Executive Sponsorship Quality — Score: 3.8 — The Lever That Makes Everything Fixable
The CEO has personally engaged in three design decisions, rescheduled board commitments to attend project reviews, and has publicly and privately described this as the organization's top priority. This is not performative sponsorship. The practical implication: the CEO has the organizational authority to hold the scope line, assign data owners, and create capacity relief — all three of the conditions required before Q1 2027 can be treated as firm. The CEO does not need convincing. The CEO needs a clear ask.
Vendor & SI Relationship — Score: 3.1 — Leverage You Can Use When Scope Pressure Arrives
The contract was negotiated with experienced commercial and legal input. Change order provisions, performance commitments, and resource continuity requirements were explicitly reviewed before signing. The internal program director has organizational authority over the SI's project manager. Meridian is running this engagement, not the other way around. When the scope conversation with the SI becomes necessary — and it will — Meridian has standing to have it on favorable terms.
Governance & Decision Velocity — Score: 2.6 — Watch, Trending Positive
Decisions are running two to four weeks on average — slower than the project requires but improving. The steering committee structure is functioning and decisions are generally holding once made. One change would move this from Watch to Strong: a named decision owner with a 48-hour escalation path for urgent design and scope decisions. That is a governance mechanism, not a cultural change. It can be in place within 60 days.
CxO Amplify

## Slide 8
Conditions for Confirming Q1 2027 Go-Live
These conditions are organized into three bands. The first band contains the launch gates — conditions that must be met before Q1 2027 is treated as firm. The second band contains risk reduction prerequisites that must be completed before sprint planning locks in assumptions. The third band contains execution controls that operate continuously once the project is running.
BAND 1 — LAUNCH GATES | Must be resolved before Q1 2027 is treated as a committed date
When
What Must Be True
Primary Owner
Immediately
Scope definition settled in leadership working session — every item in or out, documented
CTO (chair), CEO (decision authority)
Gate
Within 30 days
Named business data owners assigned for all major data domains with decision authority
COO (accountable)
Gate
Within 30 days
Clinical SME capacity relief explicitly planned and budgeted — backfill identified
COO / CFO
Gate
BAND 2 — RISK REDUCTION PREREQUISITES | Must be completed before SI sprint planning locks assumptions
Within 45 days
Data architecture gap assessment completed against Epic data model
CTO / Data Lead / SI
Req'd
Within 60 days
Fast-track decision mechanism with named owners and 48-hour SLA operational
Program Director
Req'd
Month 3
Real data migration test completed — results reviewed and plan updated
Data Owners / SI
Req'd
Month 4
End-to-end test scenarios defined with named clinical process owners
Clinical Leads / IT
Req'd
BAND 3 — EXECUTION CONTROLS | Operate continuously once the project is running
Month 6
Cutover rehearsal completed — governance for go/no-go decision formally defined
Program Director / CEO
Ongoing
Ongoing
Monthly scope discipline review — all informal requests formally evaluated and documented
Program Director / Steering Committee
Ongoing
Reassessment trigger: Once Band 1 launch gates are complete, reassess launch posture — ideally within 45–60 days. Completion of all three gates is expected to move the verdict from Not Ready to Conditionally Ready.
CxO Amplify

## Slide 9
Questions the Board Should Ask
The board does not need to own the data architecture gap assessment or the SME backfill decisions — those belong to management. But the board does need to ask four questions that distinguish between a committed launch date and a planning target. These questions create appropriate oversight without requiring technical expertise.
1
Is Q1 2027 a committed go-live date or a conditional planning target?
The distinction matters because a committed date creates organizational pressure to launch regardless of readiness. Until the Band 1 launch gates are met, the honest answer is that Q1 2027 is a target, not a commitment. The board should be clear on which it is treating it as.
Ask: CEO / CTO
2
Who has the authority to say no to scope expansion — and has that authority been used?
The existence of a governance process is not the same as the exercise of it. The board should ask not only whether a change control process exists but whether any informal scope requests have been formally evaluated and declined. If the answer is no, scope discipline is not yet operational.
Ask: CTO / Program Director
3
Which business leaders own data quality and workflow readiness — and what are they accountable for delivering, by when?
Data migration and workflow design are not IT problems. They are business problems that happen to involve technology. If no business leader can name their specific accountability for data quality or process decisions, the organizational conditions for a successful implementation are not yet in place.
Ask: COO / Department Heads
4
What operational work is being explicitly deprioritized to create capacity for the people this implementation depends on?
Every organization says this is a top priority. The question is whether the resource allocation matches the statement. If the clinical SMEs most critical to Epic's success are still carrying full operational loads, the priority is rhetorical, not operational. The board should ask for the specific trade-off decisions that have been made.
Ask: COO / CFO
CxO Amplify